## Sheet1
	Activity	Deadline	Remarks
5 feb.	First meeting
12 feb.	Meeting with the client	Plan Sprints	Begin sprint 1
19 feb.		Requirements
26 feb.	Prepare presentation
4 mrt.		P1: Initial Presentations
11 mrt.
18 mrt.			End sprint 1
25 mrt.			3rd quarter exams
1 apr.			3rd quarter exams
8 apr.			Begin sprint 2
15 apr.
22 apr.		P2: Intermediate Presentations
29 apr.			Easter vacation
6 mei		P2: Intermediate Presentations	End sprint 2
13 mei			Begin sprint 3
20 mei
27 mei
3 jun.
10 jun.		P3: Final Presentations	End sprint 3
??	Project discussions		4th quarter exams